## Read me
SSG BRD feature list for development
Source | SSG_BRD_Name&Forms_Pilot_v0.2
Covers | Two products defined in that one file: the OTC Allege pilot, and the Work Driver Onboarding Wizard platform.
Feature numbering | F-xx are OTC Allege pilot features. W-xx are Work Driver Onboarding Wizard features.
Sheet | What it holds
Features | All features, one row each, with the BRD reference each came from. Filter on Part, Product, Role, Priority, or on Repeat? to drop the repeats. Rows shaded amber are repeats that should not be built separately. IDs run in reading order; the ID map sheet gives the old number against the new one.
Overlap map | Where features in different Parts describe the same thing, and what to build once.
Open points | Contradictions and gaps in the BRD that need a business decision before or during build.
Service expectations | The non-functional requirements from both BRDs.
Not in Phase 1 | Deferred and excluded items, listed so none is built by mistake.
How the Parts relate | Part A is the behaviour of the Allege flow, capability by capability. Part B is the same system seen through each role's screens and permissions. Part C is the platform services every capability uses. Part D is the wizard platform. Phase 1 builds the Allege flow as a wizard configuration, so Part D is the engine and Parts A to C describe what that engine must do and how it is configured.
BRD coverage | Every numbered requirement and use case in both BRDs, mapped to the features that cover it.
Integrations and access | The systems the solution reads from and writes to, with the access request status from BRD 15.C.
Status column - added 30 September 2026
Assessed against the NexAI OTC application as it stands on the Nomura BSM development instance, and against the BRD (Name & Forms - OTC Allege Pilot, BRD v0.2). Every status below was checked against the delivered configuration, not against the plan.
Value | Meaning
Done | Every material part of the feature is built and working.
Partially done | Built and usable, but something specific is missing. The Comments column names what.
Not started | In scope, nothing built yet.
Later phase | The BRD itself places this outside Phase 1, so it is deliberately not built.
Not in BRD | The BRD does not support this feature as written - and it is not built. The Comments column gives the BRD reference that says otherwise.
Counts
Done | 15 of 100
Partially done | 67 of 100
Not started | 15 of 100
Later phase | 1 of 100
Not in BRD | 2 of 100
Total | 100 features

## Features
ID | Part | Section | Product | Primary role | Priority | Feature | What it does | Detail | BRD ref | Repeat? | Repeat of / overlaps | Status | Comments
F-01 | Part A. Features by capability | A1. Ingestion | OTC Allege pilot | System | High | Ingest mails from the shared mailbox | Read new emails from the OTC Settlements shared mailbox (otcsettlements@nomura.com) at a set interval and put each one in a processing queue. | 1. Poll interval is configurable: 60 minutes for the pilot, 15 minutes as the production target. 2. Save the email body, the headers, and all attachments as received. 3. Leave the original email in the mailbox as it arrived. 4. Alert the Operations team if a poll cycle fails. | 7.2, 9.2(1), UC-01 | Unique |  | Partially done | Upload-only: the "Ingest Dropped Email" flow lands each .eml as an email row and the ingest step parses headers/body. No mailbox poll, no interval config, no Ops alert.
F-02 | Part A. Features by capability | A1. Ingestion | OTC Allege pilot | System | High | Percentage switch for how much mailbox volume the solution picks up | A setting that decides what share of the eligible mail in the mailbox the solution works on, with the rest left to analysts to handle as they do today. | 1. Set as a percentage of the eligible mail arriving in the mailbox, e.g. 10% to the solution and 90% to analysts. 2. The count is per mail across the whole mailbox: of 100 mails received today, 10 reach the solution, and those 10 can be from different counterparties. 3. At 10% the solution takes every 10th eligible mail. 4. The same mail must always fall on the same side, so a retry or a re-poll never moves it. 5. Because the count is per mail, one counterparty's mail can sit on both paths during the parallel run, including a confirmation on one path and its correction on the other. 6. Can be set to 100% for full cut-over, or 0% to switch the solution off and fall back to the manual process. 7. Mail left to analysts is not picked and not tagged; it stays exactly as it arrived in Outlook. 8. Only the Admin role can change it, and every change is logged. | 7.2.1, 12.5(3) | Unique |  | Not started | No routing throttle anywhere: no percentage property, no config key, no per-mail allocation logic. BRD 7.2.1 and 12.5(iii) do call for it.
F-03 | Part A. Features by capability | A1. Ingestion | OTC Allege pilot | System | Medium | Feed the Operations end-of-day sweep that looks for missed mails | The end-of-day sweep itself is an existing Operations script that runs outside the solution. What the solution has to build is the record of what it picked up, so the script can work out what it did not. | 1. Expose the list of mails the solution picked up, with Message-ID, sender, subject, received time and outcome. 2. The Operations script compares that list against the mailbox and reports the gap; it runs at end of day or at an interval Operations sets. 3. No screen and no user journey in the solution; this is a data feed only. 4. Needed once the solution runs in shadow mode or in production. | 9.2(4) | Unique |  | Partially done | The email table holds sender, subject, classification and classification_reason (list module "Settlement Emails Relevant"). Missing: Message-ID and mailbox received time are never stored, and no feed/API is exposed.
F-04 | Part A. Features by capability | A1. Ingestion | OTC Allege pilot | System | Medium | Build ingestion so a new source is configuration, not a rebuild | TRAM, shared folders and Bloomberg chat are out of Phase 1 but are expected to become input sources later. The ingestion layer has to take a new source as configuration. | 1. A second source of the same type is set up as configuration only: if email ingestion is built for one mailbox, adding a second mailbox is a configuration entry, not a rebuild. 2. Keep source-specific handling (mailbox polling, credentials, payload shape) behind one common interface. 3. Everything downstream of ingestion works on the common internal representation, not on an Outlook object. 4. Adding a source must not require a change to identification, extraction, matching or the screens. 5. Phase 1 ships one source only, the OTC Settlements shared mailbox. | 7.10(i), 4.1 forward extensibility | Unique |  | Partially done | Intake is one source-agnostic front door (source_type/source_ref) and downstream reads only work_item/mail_* fields. But the wizard's ingestion type, mailbox and frequency are never consumed: a new source still needs a connector.
F-05 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | High | Drop mail that is not new counterparty mail | Filter ingested mail on its metadata before any content is read. | 1. Drop emails sent from Nomura internal domains. 2. Keep only newly initiated threads; do not process replies on existing threads. 3. The exact test for a newly initiated thread (no In-Reply-To header, no Re: or Fwd: subject prefix, no quoted content) is to be finalised during build. 4. Still to be decided: which signals decide new mail against reply, in what order, and what happens when the headers say new but the body carries quoted Nomura text. | 7.3 Stage 1, UC-02 | Unique |  | Partially done | identify() drops reply/forward subjects, quoted threads and noise domains, stamping a classification reason. Missing: internal senders - the noise-domain list holds only one external domain.
F-06 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | Medium | Set aside mail that needs no action | Recognise mail that reaches the mailbox but carries no trade to work, and keep it out of the analyst's queue. | 1. Bounce-backs returned by a counterparty mail server. 2. Out-of-office auto-replies. 3. Marketing mail, newsletters, regulatory notices and KYC update requests. 4. An older mail that a counterparty forwards again asking for an update. 5. The BRD assumes this volume is low and expects such mail to surface as an exception at extraction | 6.8, 7.3 note | Unique |  | Partially done | Forwarded chasers drop via the thread/reply exclusions and other mail falls out as reason no_label_match. No detection of bounce-backs, OOO auto-replies, newsletters or KYC mail - no header check or keyword configured.
F-07 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | High | Label each email by settlement timing | Compare the value date in the email against the current date and label the email accordingly. | 1. Value date in the future: label Pre-Settlement. 2. Value date is today: label Settlement. 3. Value date in the past: label Post-Settlement. 4. Record the label and the confidence score for the label. 5. Pre-Settlement and Settlement mails go on to extraction. 6. Post-Settlement mail is recognised and labelled but is not advanced to extraction. 7. There is no separate Allege label at this stage; Allege is decided later by the matcher when it finds no candidate. | 7.3 Stage 2, 4.1(1), UC-02 | Unique |  | Partially done | The dashboard yields Pre Settlement / Settlement Date / Post Settlement in the Classification column, but it compares the email's own date not today, stores no label or confidence, and runs after extraction. BRD 7.3 Stage 2 actually names SSI Verification and Confirmation Reaffirmation - neither is built.
F-08 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | Medium | Keep going when the label confidence is low | A low confidence label does not stop the item. | 1. Continue to extraction as the default path. 2. Record the low confidence identification outcome in the audit trail and also on the frontend for the analyst to view. | 9.2(3), 11.2 | Unique |  | Partially done | Classification is audited as classification.decided with a confidence level and shown on the Audit Trail page; nothing blocks the item. But identification has no score or threshold - the level is a constant High or Medium.
F-09 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | High | Identify the counterparty from the sender details | Check the from, to and cc addresses against the counterparty master (Eve) to identify the counterparty. | 1. Assign a counterparty only where the addresses point clearly to one counterparty in the master. 2. Where the sender is unknown , do not force a counterparty assignment. | 9.2(5), 6.3 | Unique |  | Partially done | The Extract Counterparty step looks the sender up in the counterparty directory by exact email address and blanks it when unknown. Missing: to/cc are not checked and there is no domain-level match.
F-10 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | Medium | Flag an unknown or ambiguous sender | Where the sender cannot be tied to one counterparty, say so on the item instead of guessing. | 1. Sender domain not present in any reference list such as Eve, i.e. a new counterparty, a broker not yet onboarded, a misdirected mail or spam. 2. Aggregator or middleware senders, where the domain serves many end counterparties. 3. Broker, sales desk or distribution list writing on behalf of a client. | 6.3 | Unique |  | Not started | Nothing flags an unknown or ambiguous sender: the counterparty name is simply left blank (no forced guess), with no flag column, no exception bucket and no aggregator or broker/DL handling.
F-11 | Part A. Features by capability | A2. Email identification and filtering | OTC Allege pilot | System | High | Assign each picked email to an analyst | Allocate every picked email to a named analyst at the point of pickup. | 1. Phase 1 uses the existing alphabet-wise mapping the team uses today. 2. The mapping is configurable through the manager view. | 7.4, 5.3, 9.3.2 | Unique |  | Partially done | Assignment is analyst-to-work-driver: assigned users are set in the manager wizard list and enforced by AccessGuard. Missing: no named analyst stamped per email at pickup, and no alphabet-wise mapping.
F-12 | Part A. Features by capability | A3. Outlook tagging | OTC Allege pilot | System | High | Tag only the mails the solution has picked up | Apply an Outlook tag to picked mail so analysts can see in Outlook what the solution is handling. | 1. The tag carries two parts: the processing stage and the assigned analyst name. 2. The assigned analyst part of the tag does not change as the item moves through the flow. 3. Mail the solution has not picked up is not tagged at all. | 7.4, UC-03 | Unique |  | Partially done | The Outlook Tagging column covers only picked (relevant) mail. Missing: no assigned-analyst part in the tag, and the wizard's 5 tagging stages are written but never consumed.
F-13 | Part A. Features by capability | A3. Outlook tagging | OTC Allege pilot | System | High | Move the tag on as the item progresses | Update the processing stage in the tag as the item changes state. | 1. Awaiting Confirmation: extraction done, analyst needs to confirm or correct the fields. 2. Awaiting review: the matcher has produced an outcome, analyst needs to review the candidates. 3. Resolved-Matched: analyst has confirmed the match, and write-back has been triggered or the cashflow has gone for the 4-eye check, per F-37. 4. Resolved-Unmatched: the analyst rejected the match output, or the matcher found nothing at all (an allege), and the analyst is working the case manually. 5. These four values are the whole tag set, and the tag reflects the state the cashflow currently sits in. 6. Each tag also carries the assigned analyst, per F-12. 7. Still to be decided: an allege and a rejected match both end as Resolved-Unmatched, so Outlook cannot tell them apart; whether a fifth tag value is added is open. | 7.4 tag taxonomy, 7.7, 7.9 | Unique |  | Partially done | All four stages are derived from the confirm/resolution fields (Awaiting Confirmation, Awaiting Review, Resolved-Matched / Resolved-Unmatched). Missing: no write-back fires behind Resolved-Matched, and no analyst in the tag.
F-14 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Extract cashflow fields from the email body | Read the email body and produce a structured record for each cashflow referenced in it. | 1. Mandatory fields to extract: counterparty name as stated in the email, currency or currency pair, notional or amount, direction (buy/sell or pay/receive), value date. 2. Other fields to extract where present: counterparty reference (alphanumeric), Nomura entity name, product (e.g. FX Forward, IRS, CDS), trade date. 3. SSI fields to extract: bank name or BIC, account number, beneficiary name or BIC, intermediary bank where present. 4. Handle the body formats counterparties actually send: free-form prose, semi-structured labelled text, tables pasted into the body, a mix of prose and table, forwarded threads with the original embedded, and reply chains with edits at the top. | 7.5, 6.1, UC-04 | Unique |  | Partially done | The extraction engine reads all 13 catalogue fields (5 mandatory, 4 optional, 4 SSI) from prose, labelled and table bodies. Missing: forwarded and reply-chain bodies are dropped as irrelevant at identification, so they never reach extraction.
F-15 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | Low | Extract cashflow details from an image in the email body | Read cashflow details out of a screenshot or image pasted into the email body and produce the same structured records as a text body. | 1. In Phase 1 scope. 2. Read all kinds of images, including screenshots, scanned documents and photographed documents. 3. Produce the same field set as a text body, with a confidence score per field. 4. Where the image cannot be read, show the failure explicitly on screen and leave the item for the analyst to work on it manually. | 6.1(7), UC-04 pre-conditions | Unique |  | Not started | No image path: the field extractor returns nothing when figures exist only in an image, and PDF discovery requires a real PDF header, so an inline screenshot is never read. BRD 6.1(7) / UC-04 pre-conditions require it.
F-16 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Extract cashflow fields from an Excel attachment | Open the Excel attachment, find the range that lists the trades, and produce one record per row. | 1. Support .xls , .xlsx , .csv 2. Map varied column headers and column orders to the standard field set. 3. Handle differing unit conventions, e.g. notional written in millions versus absolute, rates written as a percentage versus a decimal. | 7.5, 6.2(1), UC-05 | Unique |  | Partially done | The Excel extractor maps header synonyms per sheet, one record per row. Missing: the attachment gate demands the modern zip signature, so legacy .xls and .csv are rejected; no millions/percent unit handling.
F-17 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | Low | Open password-protected attachments | Accept a password-protected attachment, open it, and extract from it as normal. | 1. In Phase 1 scope. 2. The counterparty sends the password separately, so the solution looks for it in that separate mail. 3. Where the password cannot be found, or does not open the file, show the failure explicitly on screen and leave the item for the analyst to work on it manually. | 6.2(3), UC-05 pre-conditions | Unique |  | Later phase | BRD 6.2(3) and UC-05 Variations put password-protected attachments out of Phase 1, so nothing is built - no password lookup and no decrypt path. NOTE: this sheet's own Detail line says "In Phase 1 scope", which contradicts its own BRD reference - worth confirming with Nomura which is intended.
F-18 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Pick the right attachment when there are several | Work out which attachment carries the content to act on. | 1. Where an internal confirmation attachment is attached alongside the trade file, select the trade file. 2. Where cashflow details and SSI details arrive as separate attachments, identify which attachment carries which. | 6.2(4), 6.2(5), UC-05 | Unique |  | Partially done | The Excel extractor separates cashflow sheets from SSI sheets and joins SSI by currency + direction. Missing: no attachment is ever deselected - every workbook and PDF is read and merged by the de-duplicator.
F-19 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Create one record per cashflow under the parent email | Treat every cashflow in the email as its own record, linked to one parent email reference. | 1. One email can carry several cashflows, and each becomes its own child record. 2. Where the counterparty states a summary in the body and the individual cashflows in an attachment, the body gives the parent and the attachment gives the children, under one parent reference. 3. Each child record is matched and tracked independently. 4. Child records stay grouped under the parent for analyst view and audit. 5. The parent email closes when all child records are resolved. 6. Where child records end with different outcomes, show a mixed status on the parent. | 7.5, 6.7, UC-15 | Unique |  | Partially done | One cashflow per trade under the email reference; each is confirmed, matched and resolved alone, and the case screen groups them. Missing: no parent closure when all children resolve, and no mixed status on the parent.
F-20 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Score confidence per field and flag the weak ones | Produce a confidence score for every extracted field and flag the ones below threshold. | 1. Flag the field visually in the analyst view; do not block the workflow. 2. Threshold values are configurable per product. | 7.5, 11.1, 11.2 | Unique |  | Partially done | Confidence grades all 13 fields (grounding + validation) and the case screen badges each one non-blockingly. Missing: the levels are hard-coded High/Medium/Low, with no configurable per-product threshold.
F-21 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | High | Standardise the data before matching | Convert dates, amounts, rates and currencies into a consistent format before the matcher runs, so that differences in how counterparties write the same value do not cause false mismatches. | 1. Dates into one internal format, whatever the counterparty wrote: 30-May-26, 30/05/2026, May 30 2026. 2. Amounts into absolute values, so 50M, 50,000,000 and 50 mio all become the same number. 3. Rates into one convention, percentage against decimal. 4. Currencies into ISO codes, and currency pairs into one order. 5. Counterparty and entity names into the master form, using F-28. 6. Standardise before the matcher runs, so that a difference in how a value was written never shows as a mismatch. | 9.2(4) | Unique |  | Partially done | Validation normalises dates to ISO, amounts to plain numbers and currency to ISO before matching. Missing: no rate convention (there is no rate field at all), no currency-pair ordering, and no 50M / mio magnitude scaling.
F-22 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | Low | Handle non-English and mixed-language content | Process emails that are not in English, for example German and Japanese, and emails that mix languages, without losing accuracy. | 1. Covers a bilingual body, and an English body with a local-language attachment. | 6.4, 5.7 | Unique |  | Not started | No language handling: the identification keywords and all 13 field prompts are English-only, and the extraction guardrail forbids translation. Only header and UTF-8 decoding exist. Not measured against a real non-English mail.
F-23 | Part A. Features by capability | A4. Field extraction | OTC Allege pilot | System | Low | Process the supported part and hand the rest to the analyst | Where an email mixes supported and unsupported content, work the supported part and surface the rest rather than rejecting the whole email. | 1. Example: trade details in the body with a PDF attached. Process the body, flag the PDF for the analyst. 2. Flag for analyst handling: PDF attachments, email-as-attachment (.msg), empty or corrupt attachments, and trade details held behind a link to a counterparty portal. 3. Images in the email body and password-protected attachments are no longer flagged out; they are processed under F-15 and F-17. | 9.2(8), 6.1(8), 6.2 | Unique |  | Partially done | Body and every PDF are both extracted and merged, and a short read sets the email extraction status to partial - surfaced by the Exceptions view on bsmdev. Missing: no detection or flag for .msg, empty/corrupt attachments, or portal-link content.
F-24 | Part A. Features by capability | A5. Analyst confirmation of the extraction | OTC Allege pilot | System | High | Analyst confirms the extracted fields before matching | Show the extracted fields to the analyst and run the match only after the analyst confirms them. | 1. The analyst can confirm as extracted, or correct individual fields. 2. Save both the original extracted value and the corrected value, with the time and the analyst name. 3. For an email with several cashflow, the analyst confirms each cashflow separately; one cashflow does not hold up another. 4. Allow a bulk confirm where all trades in an email are correct, logging each one individually. 5. The matcher never runs on unconfirmed extracted fields. | 7.6, UC-06 | Unique |  | Partially done | Per-cashflow confirm sets the confirmed flag; the match flow and the case screen both gate Compare & Match on it, and an override audits AI value, analyst value, actor and time. Missing: no bulk confirm (UC-06 Variations).
F-25 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | High | Tier 1: exact match | Search the settlement system for a single exact candidate using the analyst-confirmed fields. | 1. Where the email carries a counterparty reference, search on that reference together with the confirmed economic fields: amount, value date, currency, direction, Nomura entity, counterparty entity. 2. Where there is no counterparty reference, or the reference search returns nothing, search on the confirmed economic fields only, still filtering on counterparty entity. 3. Mark as Matched where exactly one candidate is returned and its status is not settled. 4. Where several candidates are returned, show all of them to the analyst. 5. Where nothing is returned, go on to Tier 2. | 7.7, UC-07 | Unique |  | Partially done | Tier 1 is an exact match on currency + direction + value date + amount + counterparty over the booking table. Missing: the counterparty-reference search leg (the reference is display-only), the not-settled filter, and Nomura entity.
F-26 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | High | Tier 2: match with tolerance | If the exact match finds nothing, search again with small allowances on some fields. | 1. Allow fuzzy match on counterparty name and Nomura entity name. 2. The counterparty name is still used here, only matched loosely, e.g. JPM Chase NY against JPMORGAN CHASE BANK NA. This is not the same as Tier 3, which stops using the counterparty altogether. 3. Allow notional within plus or minus $50 equivalent. 4. Allow value date within plus or minus 2 business days. 5. Keep all other fields exact. 6. When counting business days, skip Saturdays, Sundays, bank holidays (source: Takara) and currency holidays (source: Thomas Murray). 7. Worked example from the BRD: value date 5 May 2026 (Monday), 6 May a bank holiday, 7 May a currency holiday, so the search window is 1 May to 9 May. 8. Show every candidate found as a potential match, closest first; where the differences are equal in size, show the positive difference before the negative. 9. Show the field-by-field differences, the tier that produced the candidate, and a confidence indicator. 10. Still to be decided: the rate source and the as-of date used to convert a non-USD notional before the plus or minus $50 test is applied. | 7.7, UC-08 | Unique |  | Partially done | Tier 2 applies a configurable absolute amount tolerance (50), a 2-business-day value-date window and 0.85 name fuzzy; candidates rank closest-first with the deltas, tier and confidence shown. Missing: holiday calendar, and no FX-equivalent tolerance.
F-27 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Tier 3: search without the counterparty | If Tier 2 finds nothing, drop the counterparty filter and search on the remaining fields. | 1. The counterparty is not used as a filter at all here, which is the difference from the fuzzy name match in Tier 2. 2. Covers cases where the counterparty name in the email does not resolve cleanly to the master, or the trade sits under a counterparty alias. 3. Flag the counterparty mapping on each candidate for the analyst to validate. 4. Tier 3 candidates always need analyst validation and are never resolved automatically. 5. Where nothing is found, mark the cashflow Unmatched / Allege. | 7.7, UC-09 | Unique |  | Done | Tier 3 drops the counterparty and keeps amount + value date exact; candidates list under "Tier 3 - counterparty-less" with the counterparty cell flagged red, nothing auto-selects, and no candidate shows the Allege banner.
F-28 [overlaps F-09, F-21] | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Resolve counterparty trading names to the one entity in the master | The counterparty writes its name free-hand in the email. Map that text to the single official legal entity held in the counterparty master before matching. | 1. Example from the BRD glossary: JPM Chase NY maps to JPMORGAN CHASE BANK NA. 2. This is a different input from F-09, which reads the sender address. Here the input is the name text in the body, and the two can disagree, e.g. a broker sends on behalf of a client. 3. Needed for the Tier 1 counterparty filter, for the fuzzy name match in Tier 2, and for validating a Tier 3 candidate. 4. Build it once as a single counterparty resolution service used by F-09, F-21 and the matcher. | 5.7, 7.7 Tier 3, glossary | Overlaps | F-09, F-21. Same counterparty resolution service, reached from a different input. | Partially done | The counterparty directory resolves the sender address to an organisation name only. The body name is used verbatim (normalised across rows) plus the Tier 1/2 fuzzy compare; no name-to-master alias resolution exists.
F-29 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Hold the Nomura entity list | Hold the mapping of Nomura entity short forms to their long descriptions and use it in extraction and matching. | 1. The BRD supplies the list, for example NIP is Nomura International Plc and NGFP is Nomura Global Financial Products Inc. 2. Counterparties write either form, so both must resolve to the same entity. | 15.D, 7.5, 7.7 | Unique |  | Not started | No Nomura-entity table and no short-form/long-form mapping. The extracted entity is free text and the booking table has no entity column, so the entity is never used in matching. (The BRD has no appendix 15.D; 7.5 and 7.7 are the real basis.)
F-30 [overlaps F-26] | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Maintain the bank and currency holiday calendars | Hold the holiday calendars the value date tolerance depends on, and keep them current. | 1. Bank holidays from Takara. 2. Currency holidays from Thomas Murray. 3. Used by the plus or minus 2 business day tolerance in F-26; built once, as a calendar service. 4. Needs a refresh routine and a check that the calendar is current, or the tolerance window goes wrong silently. | 7.7 | Overlaps | F-26. The reference data the plus or minus 2 business day tolerance in F-26 depends on. | Not started | No holiday calendar table or service. The date-tolerance helper skips Saturday and Sunday only; the missing Takara / Thomas Murray calendars are recorded as a known gap in the code beside the tolerance constant.
F-31 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | High | Compare the SSI once the cashflow is found | After the cashflow is fetched from PCM, compare the SSI held on that cashflow against the SSI extracted from the email. | 1. SSI details are not used to find the cashflow in the initial search. | 7.7 | Unique |  | Not started | No SSI comparison: the booking table has no SSI columns and the comparator covers only counterparty, value date, amount, currency and direction. SSI is extracted and shown on the case screen but never compared.
F-32 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Handle netted entries leg by leg | Where PCM holds a netted entry, work each entry of the net separately. | 1. An allege on one leg of a net is worked on that leg even when the other leg does not match. | 7.7 | Unique |  | Done | Each cashflow is matched, stored, selected and resolved independently, so an allege on one leg is worked even when the other leg does not match. The Gross/Net switch built on bsmdev adds the other direction - a mail stating a net total can settle as one cashflow instead of every leg.
F-33 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | High | Present the match outcome to the analyst | Show the outcome, the tier that produced it, and a confidence indication. | 1. Matched: exact Tier 1 hit with status not settled. 2. Matched-but-Settled: Tier 1 hit but the cashflow is already settled in Nomura's system, shown as its own exception type. 3. Fuzzy Match: Tier 2 candidate within tolerance, with the field-level differences shown. 4. Counterparty-less Candidate: Tier 3 candidate found by ignoring counterparty. 5. Aggregate scenario, where the counterparty asserts one trade and Nomura holds several child trades summing to it, or the reverse: show as unmatched in Phase 1. 6. Unmatched / Allege: no candidate found. This outcome is what makes a cashflow an Allege. | 7.7, UC-13 | Unique |  | Partially done | The candidate table shows the producing tier, High/Medium/Low confidence, per-field diffs and the Allege banner. Missing Matched-but-Settled: the booking status is read into the candidate object but never tested or displayed.
F-34 [overlaps F-26] | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Make the matching rules configurable | Allow the business to change matching rules and tolerances per product through an admin screen, without a code release. | 1. Covers the Tier 2 ranges and the field-level matching behaviour. | 9.2(6) | Overlaps | F-26. F-26 states the tolerance values; F-34 requires them to be configurable. | Partially done | Builder step 5 writes the value-date, amount and name-fuzzy tolerances per work driver, read live by the matcher. Scoped per work driver rather than per product; the per-field match mode is captured in the builder model but never read.
F-35 | Part A. Features by capability | A6. Compare and Match | OTC Allege pilot | System | Medium | Queue items for matching when a settlement system is down | Where a settlement system is unavailable, allow extraction and analyst confirmation to carry on and hold the cashflow in a queue to be matched when the system is back. | 1. Extraction and analyst confirmation carry on as normal while the settlement system is unavailable. 2. The confirmed cashflow is held in a queue instead of failing. 3. The matcher runs the queued cashflows when the system is available again, oldest first. 4. The analyst can see that the cashflow is queued and why, so it does not look lost. 5. This is the availability case; a genuine failure mid-flow is F-69. | 9.5(3) | Unique |  | Not started | No matching queue or retry. Bookings are a local golden-source table and nothing defers, holds or replays a match on settlement-system availability, nor shows a queued state to the analyst.
F-36 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | High | Confirm a matched cashflow and write back | On analyst confirmation, write the cashflow status back to NEWS and the settlement system under the analyst's own identity. | 1. Nothing is written back without analyst confirmation; no cashflow is resolved automatically. 2. Where the cashflow is at or above the value threshold of $5 million, the solution routes it for the 4-eye check instead of writing back straight away, per F-37. 3. The 4-eye control itself does not change: same threshold, same two-person rule, same outcome. What changes is that the solution initiates and tracks the hand-off instead of the analyst arranging it outside the solution. 4. Maker-checker and value threshold authorisation for anything outside that route continue to run as they do today. | 7.8, UC-10, 9.3.1(iii) | Unique |  | Partially done | Nothing resolves without the analyst: resolve sets the resolution and audits a write-back event under the user's identity. Nothing is pushed though - "Send to NEWS" is a status line; no external write-back exists.
F-37 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | High | Route an above-threshold matched cashflow to the manager for the 4-eye check | Where a confirmed match is at or above the value threshold, push the cashflow to the manager's view for the second pair of eyes instead of leaving the analyst to arrange it outside the solution. | 1. Triggered on analyst confirmation of a match where the cashflow value is at or above the threshold ($5 million). 2. The cashflow appears in a pending 4-eye queue in the manager's view, with the analyst's confirmation and the full trail attached. 3. The checker is the manager. This is the manager's only action right: approve or reject an item in the 4-eye queue. The manager stays read-only everywhere else. 4. Write-back happens only after the checker has approved; a rejection returns the cashflow to the analyst. 5. The checker cannot be the analyst who confirmed it. 6. Both the confirmation and the approval are recorded with identity and timestamp. 7. The control is not being changed, only enabled through the solution, so the BRD lines that say the control sits outside the UI and that the hand-off is manual need correcting: 9.3.1(iii) and UC-10 step 3. The lines that say the control is preserved unchanged stay as they are. | 7.8, 9.3.1(iii), UC-10 step 3 | Unique |  | Not in BRD | BRD 9.3.1(iii) places 4-eye / value-threshold controls outside the solution and its UI, and UC-10 step 3 has the analyst do it manually. Nothing built: no threshold, no 4-eye queue, and the manager role stays read-only. (The BRD's own threshold figure is inconsistent: $5m in 7.8/5.8 vs "e.g. $500K" in UC-10.)
F-38 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | High | Accept or reject a fuzzy candidate | Let the analyst accept a Tier 2 candidate, which sends it down the write-back path, or reject it. | 1. On rejection the cashflow returns to unmatched and follows the unmatched workflow. | 7.8, UC-11 | Unique |  | Done | Selecting a candidate stores the chosen booking and outcome (audited) and feeds the resolve path; No match sets the outcome to no_match (audited) and returns the item to the unmatched flow.
F-39 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | Medium | Handle a Matched-but-Settled exception | Give the analyst the two actions this exception needs, and record what was done. | 1. Show the candidate as already settled in Nomura's books, on the candidate itself, not only as a bucket label. 2. Do not offer confirm, and do not offer release, on a settled candidate. 3. Offer only the two actions this exception needs: reply to the counterparty with proof of settlement, or escalate to Front Office. 4. Record which of the two was taken. 5. Where one email produces several matched-but-settled hits, handle each cashflow separately. | 7.8, UC-13 | Unique |  | Not started | No Matched-but-Settled handling: the booking status is never tested, the settled state is not shown on the candidate, confirm/release are not suppressed, and Front Office is not in the write-back action list.
F-40 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | Medium | Record the action taken on a cashflow, whatever the outcome | Let the analyst record what was done, so any cashflow can be aged, reported and audited on the action taken and not only on its match outcome. | 1. Applies to every outcome: matched, matched-but-settled, fuzzy accepted or rejected, unmatched and allege. 2. Actions such as queried counterparty, escalated to Middle Office, escalated to Front Office, awaiting response, proof of settlement sent. 3. Phase 1 provides a record-keeping surface only; the solution does not draft counterparty mail. 4. The item stays in the Open or Critical bucket until it is resolved. | 7.8, UC-12 | Unique |  | Partially done | The audit trail records outcome, resolution and the action taken per cashflow, but the action list is fixed to NEWS / Counterparty / Middle Office - no FO escalation and no awaiting-response state.
F-41 | Part A. Features by capability | A7. Analyst action and write-back | OTC Allege pilot | System | High | Set the Outlook tag from the match outcome | Move the tag on the picked email according to what the analyst decided. | 1. Analyst confirms the candidate, with or without changes: Resolved-Matched. 2. Analyst rejects the candidates: Resolved-Unmatched. | 7.7, 7.9 | Unique |  | Partially done | Resolve sets the resolution to resolved-matched / resolved-unmatched and the dashboard shows both; the wizard holds the Outlook tagging configuration. No mailbox write exists, so no tag is ever set on the email itself.
F-42 | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | High | One screen with work grouped into buckets | Give the analyst a single place to see every cashflow in flight, grouped into buckets. | 1. Buckets: Open (being processed, awaiting analyst action), Critical (needs elevated attention), Resolved (action complete). 2. Within each bucket, sort by trade value highest first, then by ageing. 3. Show only the action options valid for the current state of the cashflow. | 7.9, 9.3.1(i) | Unique |  | Partially done | One board with status tiles acting as filters and sortable Amount / Time Elapsed; but no Open / Critical / Resolved buckets (those exist only as Manager Dashboard counts) and no default value-then-ageing sort.
F-43 [overlaps F-33] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | High | Source email and candidates side by side | Show the analyst what the counterparty sent and what the matcher found. | 1. The originating email with its parent reference ID, and child trade records grouped under it. 2. Each match candidate with its field-level differences and the tier that produced it. | 7.9 | Overlaps | F-33. The display side of the match outcomes defined in F-33. | Done | The case screen puts the mail contents beside the extracted fields, cf N-of-M navigation groups a mail's cashflows under it, and each candidate carries per-field flags plus the tier label.
F-44 [overlaps F-20] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Medium | Show AI output as a recommendation, not an answer | Mark every AI output visibly as a suggestion, and keep the AI's value and the analyst's value on screen together. | 1. Applies to three AI outputs: the settlement timing label from F-07 (Pre-Settlement, Settlement or Post-Settlement), the extracted fields, and the match candidates. 2. The two values shown together are the value the AI suggested and the value the analyst confirmed or corrected. 3. Both stay visible in the trail afterwards, not only at the moment of confirming. | 9.3.1(ii) | Overlaps | F-20. The display rule for the confidence scoring built in F-20. | Done | Every extracted field carries an AI provenance chip plus a High/Medium/Low confidence badge; candidates show tier and confidence; audit rows keep the AI-recommended value beside the analyst value permanently.
F-45 [overlaps F-60] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Medium | Full processing trail per cashflow | Show everything the solution and the analyst have done to a cashflow, in one trail. | 1. Ingestion timestamp. 2. Identification label, with classifier version and confidence. 3. Extraction inputs and outputs, with field-level confidence. 4. Analyst confirmations and corrections, with the original value, the corrected value, the time, and the analyst name. 5. Match attempts and their outcomes by tier. 6. The final action taken. | 7.9, 10.1(1) | Overlaps | F-60. The analyst-facing view of the audit store built in F-60. | Partially done | The Audit Trail view reconstructs classification, extraction, overrides (AI vs analyst value, actor, time), the match tier and write-back. Missing: no ingestion event, and confidence is one level per record rather than per field.
F-46 [overlaps F-54] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Medium | Personal queue and team queue | Give the analyst their own queue and a view of the team queue. | 1. The analyst gets their own queue and, where it is switched on, a view of the team queue. 2. The analyst can action only the cashflows in their own queue. The team queue is view only: the analyst can see another analyst's cashflows but cannot confirm, correct, reject or write back on them, because ownership of a cashflow is itself the control. 3. Team queue visibility is configurable, so it can be switched off and the analyst sees only their own work. 4. The manager's read-only view across the team is a different thing, built in F-51. 5. Still to be decided: who switches team queue visibility on or off, and whether it is set per team or per analyst. | 9.3.2, 9.2(9) | Overlaps | F-54. A consequence of the access model in F-54. | Partially done | The assignee list plus AccessGuard give the analyst a personal queue only - the landing page lists just their assigned drivers. No analyst team queue and no visibility toggle; seeing another analyst's work needs the manager role.
F-47 | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Medium | Show the counterparty's credit compliance status | Display the counterparty's credit compliance status on each cashflow, taken from the credit risk system (Takara). | 1. Values: compliant, not compliant, watch. 2. The indicator is for information only; it does not block or change the analyst's workflow. | 9.2(11), 10.1(4) | Unique |  | Not started | No credit-compliance data anywhere: the counterparty directory holds only organisation, entity and email address, and no Takara or compliance/watch value appears in the app or on the case screen.
F-48 [overlaps F-42, F-56] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Medium | Track how long each cashflow has been open | Age every cashflow from ingestion so ageing can be shown, sorted on, and reported. | 1. Feeds the secondary sort inside each bucket. 2. Feeds the ageing breach measure in the success metrics. 3. The ageing rules themselves are admin-configurable. | 7.9, 14.1, 9.3.2 | Overlaps | F-42, F-56. Ageing feeds the buckets in F-42 and is configured through F-56. | Partially done | Each row is aged from the mail's Date header (sortable Time Elapsed; the manager view shows the oldest per analyst). Missing: no configurable ageing rule and no ageing-breach measure.
F-49 [overlaps F-42] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | Low | Move a cashflow into Critical automatically | Put a cashflow in the Critical bucket where it is marked critical in Eve or Takara. | 1. Also covers items the business treats as needing elevated attention, e.g. Matched-but-Settled exceptions, low confidence extractions on high value trades, and ageing items. | 9.2(7), 7.9 | Overlaps | F-42. One of the rules that moves an item into a bucket defined in F-42. | Partially done | Critical exists only as a Manager Dashboard count of open cashflows at no-match or mismatch. No external criticality input, no Critical bucket on the analyst board, and no ageing or low-confidence rule.
F-50 [overlaps F-36] | Part B. Features by role | B1. Analyst | OTC Allege pilot | Analyst | High | Stop the analyst screen at the match outcome | Present the cashflow up to matched or unmatched and no further; the analyst then continues in their existing workflow. | 1. The analyst screen presents the outcome and the confirm or reject action, and stops there. 2. Where the 4-eye check applies, the screen hands the cashflow to the manager's queue rather than asking the analyst to arrange the check outside the solution, per F-37. 3. Maker-checker and value threshold authorisation outside that route remain outside the screens. | 9.3.1(iii) | Overlaps | F-36. Restates the control boundary already set in F-36. | Done | The case screen ends at step 3 Decide next action with Resolved - Matched / Resolved - Unmatched plus the wizard-configured write-back; nothing auto-settles and no post-trade control appears in the UI.
F-51 | Part B. Features by role | B2. Manager | OTC Allege pilot | Manager | Medium | Read-only view across the team's queues | Let the manager see the team's Open, Critical and Resolved buckets. | 1. Shows the team's Open, Critical and Resolved buckets, for every analyst in the manager's team. 2. Read-only throughout, with one exception: the pending 4-eye queue, where the manager approves or rejects, per F-37. 3. Gives visibility of team workload and of how long exceptions have been open. | UC-14, 9.3.2 | Unique |  | Partially done | The Manager Dashboard shows Open / Resolved / Critical counts per work driver plus per-analyst pending, each linking to that analyst's board in read-only mode. The three cards are static counts, not openable buckets.
F-52 [overlaps F-45, F-54] | Part B. Features by role | B2. Manager | OTC Allege pilot | Manager | Medium | Drill into any cashflow without being able to action it | Let the manager open any cashflow and read the full processing trail and the analyst actions taken. | 1. The manager can open any cashflow belonging to their own team and read the full trail and the analyst actions taken. 2. The manager cannot confirm matches, cannot override extractions, and cannot trigger write-back. 3. The one action the manager has is approving or rejecting a cashflow in the 4-eye queue, per F-37. 4. The manager cannot change AI thresholds, tolerances, the routing percentage, or any other admin setting. | UC-14, 9.3.2 | Overlaps | F-45, F-54. The manager's view of the trail in F-45, under the access model in F-54. | Partially done | Read-only is genuinely enforced: the act-on-cashflow guard ignores manager and admin, the case screen shows "Read-only - Manager view", and the audit page gives the trail. One exception: the manager's wizard builder edits the Tier-2 tolerances.
F-53 | Part B. Features by role | B2. Manager | OTC Allege pilot | Manager | Medium | Manage the counterparty to analyst mapping | Let the manager maintain the mapping that decides which analyst gets which counterparty's mail. | 1. Phase 1 starts from the existing alphabet-wise mapping. 2. The manager is the single owner of this mapping; it is not also editable by the admin. 3. Changes are logged. | 9.3.2, 7.4, 12.2 | Unique |  | Not started | Only work-driver-to-analyst assignment exists (the Assign analysts modal). No counterparty-to-analyst mapping and no alphabet rule. Assignment changes are now captured by native record auditing on the wizard table on bsmdev, but that trail is admin-only.
F-54 | Part B. Features by role | B3. Admin | OTC Allege pilot | Admin | High | Role-based access through existing SSO and RBAC | Control what each user can see and do from their assigned role, using Nomura's existing RBAC and SSO. | 1. Roles for the pilot: analyst, manager, admin. 2. A user holds one role per session. | 9.2(9), 9.3.2 | Unique |  | Partially done | Two application roles plus 57 ACLs and AccessGuard; the login widget does SSO. Missing: no application admin role (the platform admin stands in), and the demo-users property grants manager-level view outside RBAC.
F-55 | Part B. Features by role | B3. Admin | OTC Allege pilot | Admin | Medium | Configure the AI confidence thresholds | Set the confidence threshold at each AI decision point, per product. | 1. Three decision points: email identification, field extraction, and match candidate scoring. 2. Per product means the threshold is set separately for FX Forward, IRS, CDS and so on, because a short FX confirmation and a long IRS confirmation do not extract with the same reliability. 3. Admin is the only role permitted to change thresholds. 4. A threshold change does not apply retrospectively to cashflows already in flight. 5. The threshold values themselves are to be set during the build phase. 6. Still to be decided: the threshold values themselves, per gate and per product. | 11.2, 11.3 | Unique |  | Not started | No configurable threshold at any of the three gates: confidence is derived High/Medium/Low from grounding and validation, and the matcher buckets at hard-coded 85/65. Nothing is per product.
F-56 | Part B. Features by role | B3. Admin | OTC Allege pilot | Manager | Medium | Configure the tag taxonomy and the ageing rules | Maintain the Outlook tag set and the rules that decide when an item counts as ageing. | 1. Maintain the Outlook tag set: the four values, and their meaning. 2. Maintain the ageing rules: when an item counts as ageing, and when ageing pushes it into Critical. 3. Both sit with the manager, not the admin: ageing thresholds and tag meanings are operational judgements the manager is closest to. 4. The manager's configuration scope is therefore the counterparty to analyst mapping (F-53) plus this screen. Everything else stays with the admin. 5. A change applies from the moment it is made and does not rewrite tags already applied. 6. Changes are logged, per F-63. 7. Note for the build: the tag set is system-wide, so a change made by one manager changes what every analyst sees in Outlook and what the audit trail records. Scope the screen so a manager edits only their own team's ageing rules, and treat a tag-set change as global. | 9.3.2 | Unique |  | Partially done | The four tag values appear only as the derived workflow-status column; the wizard's tagging configuration has no editing UI, and no ageing rules exist anywhere. (BRD 9.3.2 places both with the Admin, not the manager as the sheet states.)
F-57 [repeat of F-02] | Part B. Features by role | B3. Admin | OTC Allege pilot | Admin | n/a, repeat | Configure the routing percentage | Set what share of in-scope mail the solution picks up, including full cut-over and rollback to 0%. | 1. Owned by Settlements Operations leadership and applied through the admin screen. | 7.2.1 | Repeat | F-02. The admin screen for a setting already defined in F-02. | Not started | No routing or percentage control exists - the config table holds only extraction, match and spreadsheet keys, and every rule-matching mail is processed. BRD 7.2.1 does require it.
F-58 [repeat of F-34] | Part B. Features by role | B3. Admin | OTC Allege pilot | Admin | n/a, repeat | Configure the match tolerances | Set the Tier 2 tolerance values and the field-level matching behaviour, per product. | 1. Still to be decided: the tolerance values themselves, per product. | 9.2(6), 7.7 | Repeat | F-34. Same configurability requirement, stated twice in the BRD. | Partially done | Builder step 5 writes the three Tier-2 tolerances into the config overrides, read live by the matcher. But it is scoped per work driver rather than per product, and sits with the manager.
F-59 [repeat of F-54] | Part B. Features by role | B3. Admin | OTC Allege pilot | Admin | n/a, repeat | Admin cannot action individual cashflows | Restrict the admin role to configuration only. | 1. The admin has configuration screens only. 2. No confirm, no override, no write-back, and no access to an individual analyst's queue for action. 3. Enforced through the same role model as F-54, not as a separate permission layer. | 9.3.2 | Repeat | F-54. A statement of the access model, not a separate build. | Partially done | The act-on-cashflow guard has no manager/admin short-circuit, so an admin cannot confirm, override or write back in the portal. But the cashflow write ACL allows admin override, so a platform admin can still edit rows natively.
F-60 | Part C. Cross-cutting features | C1. Audit and traceability | OTC Allege pilot | System | High | Record every system action and every AI inference | Capture a complete audit trail for each processed item. | 1. Capture the input received, the AI recommendation, the confidence score, the model version, and the prompt reference where applicable. 2. Capture the analyst's confirmation or correction, with the time and the analyst's identity. 3. Capture configuration changes. 4. Retain AI audit data alongside the standard audit trail, not in a separate store, under Nomura's existing retention framework. | 9.2(10), 9.4, 12.3 | Unique |  | Partially done | Append-only event store, 11 event types and 1,712 events, each carrying actor, AI value vs analyst value, model version and prompt reference plus hash. Native record auditing was switched on for 8 tables per scope on bsmdev, so the AI trail now sits alongside the standard one. Missing: configuration changes are never written into it (the columns exist, unused).
F-61 | Part C. Cross-cutting features | C1. Audit and traceability | OTC Allege pilot | System | Medium | Log why the AI decided what it decided | Store the AI's reasoning at the point of inference, so an outcome can be explained later. | 1. Identification: the dominant signals behind the label, e.g. subject line keywords and content patterns. 2. Extraction: the passage in the body or the cell reference in the Excel that produced each field. 3. Candidate scoring: the field-level differences used to rank each candidate from closest to furthest. | 12.6 | Unique |  | Partially done | The trail stores a coarse reason code (rule match / AI context) plus prompt and input hashes. Missing: the source passage behind each field and the per-candidate field differences are recomputed at view time, never stored - so they cannot be reproduced for a past decision.
F-62 [overlaps F-60] | Part C. Cross-cutting features | C1. Audit and traceability | OTC Allege pilot | System | Medium | Reconstruct any cashflow end to end for audit | Allow Internal Audit to retrospectively rebuild, for any cashflow, the input received, the AI recommendations made, the analyst's confirmation or correction, the match attempted, and the action taken. | 1. F-60 captures the data; this feature is the ability to get it back out for one cashflow, in one place, on demand. 2. Given a cashflow, produce the input received, the AI recommendations with model version and confidence, the analyst's confirmation or correction, every match attempt by tier, and the final action. 3. Needed because audit asks about one cashflow months later, and capture alone does not make that answerable. 4. Internal Audit is the user, so it has to be readable without a developer running queries. 5. Covers the override comparison and the configuration history as at the time of the event. | 10.1(1), 10.1(2) | Overlaps | F-60. An audit query over the store built in F-60. | Partially done | The audit page rebuilds one cashflow's trail read-only - AI values, confirm/override, match tier, action - with no developer needed, and the bsmdev three-level drill reaches it from the Exceptions view. Missing: the configuration as at the time of the event, and only the producing tier is recorded rather than every attempt.
F-63 [overlaps F-60] | Part C. Cross-cutting features | C1. Audit and traceability | OTC Allege pilot | System | Medium | Keep the history of configuration changes | Hold a history of changes to the routing percentage, the confidence thresholds, the match tolerances and the other configurable values, with an effective-from timestamp on each. | 1. Every change records what changed, the old value, the new value, who made it, and the effective-from timestamp. 2. Covers the routing percentage, the confidence thresholds, the match tolerances, the tag taxonomy and the ageing rules. 3. Held in the same audit store as F-60, not in a separate log. 4. Has to be reconstructible, i.e. it must be possible to show what the configuration was on a given date. | 10.1(3), 12.3 | Overlaps | F-60. Configuration history held in the audit store built in F-60. | Partially done | Native record auditing on the config and wizard tables (bsmdev, 26 Sept) now captures every tolerance and configuration change with old value, new value, actor and timestamp, and is reconstructible to any date. Missing: it is not held in the same store as the AI trail, no explicit effective-from, and it is admin-only - not readable by Internal Audit in the portal.
F-64 | Part C. Cross-cutting features | C2. AI quality and control | OTC Allege pilot | System | Medium | Report on analyst overrides | Make override patterns reportable so model performance can be assessed. | 1. Override rate per AI component, e.g. how often the extracted notional is corrected. 2. Override rate per counterparty. 3. Override rate per product. | 11.5 | Unique |  | Partially done | An overall override rate exists on the audit widget and the AI Usage page (overrides against extractions). Missing: no per-component, per-counterparty or per-product breakdown - override rows carry no product.
F-65 | Part C. Cross-cutting features | C2. AI quality and control | OTC Allege pilot | System | Low | Surface any performance drift as a signal | Where AI performance degrades over time without a configuration change behind it, raise it for investigation rather than waiting for an incident. | 1. Signals to surface: a spike in override rate, an accuracy drop on a specific counterparty or product, a fall in average classifier confidence, and sustained extraction failures pointing to a changed counterparty format. | 11.5, 13.4 | Unique |  | Not started | No drift signal anywhere - no scheduled job, threshold check or alert over the audit or LLM-usage data. The AI Usage page shows override rate and confidence mix per date range, but nothing is ever raised for investigation.
F-66 | Part C. Cross-cutting features | C2. AI quality and control | OTC Allege pilot | System | Medium | Run in shadow mode | Process real counterparty mail alongside the analyst's manual workflow, without affecting anything downstream. | 1. BRD 13.3: the solution runs against real counterparty emails, outputs are captured for comparison against the analyst's manual handling, with no write-back and not as the analyst's primary work view. 2. Capture the outputs so they can be compared against what the analyst did manually. 3. No write-back to NEWS or the settlement systems. 4. Results are not the analyst's primary work view while in shadow mode. 5. Still to be decided: how long shadow mode runs and what has to be true to move to live; BRD 13.3 leaves this with Haris. | 13.3, 12.1(3), 14.2 | Unique |  | Partially done | Real counterparty mail is processed and the outputs are captured, and no write-back fires. But that last point is incidental - there is nothing to write back to yet, not a control. Missing: no shadow/live switch, and the analyst's manual handling is never captured to compare against.
F-67 | Part C. Cross-cutting features | C2. AI quality and control | OTC Allege pilot | System | Medium | Evaluate against the golden dataset before a change goes out | Run the AI against the golden dataset and compare the output against the known correct answers before any new prompt or example set is deployed. | 1. The golden dataset holds the email itself, the expected label, the expected field values per trade, and the expected match outcome per tier. 2. A configuration that does not meet the agreed minimum accuracy is not deployed. 3. The dataset is owned by Settlements Operations and refreshed periodically. | 13.1, 13.2, 12.4 | Unique |  | Not started | No golden dataset in the application - no store of expected labels, values or match outcomes - no accuracy comparison and no deployment gate. The builder's Test/Run only extracts a pasted sample for eyeballing.
F-68 | Part C. Cross-cutting features | C2. AI quality and control | OTC Allege pilot | System | Medium | Hold model and prompt versions, with rollback | Keep track of which model and prompt produced each inference, and be able to go back to an earlier one. | 1. Record the model version and the prompt reference against every inference. 2. Support fail-over to a previous model version as a containment step. 3. Record an effective-from timestamp on every change. | 12.3, 12.4, 12.5 | Unique |  | Partially done | Every extraction inference records the model version, a prompt reference and a prompt hash, plus the model per call in the usage table. Missing: no version registry and no rollback control, and the effective-from timestamp is never written.
F-69 [overlaps F-01] | Part C. Cross-cutting features | C3. Resilience and failure handling | OTC Allege pilot | System | Medium | Handle a processing failure without losing the item | Where the solution fails mid-flow, keep the item with the analyst and make the failure visible. | 1. Covers extraction errors, a settlement system being unavailable, and write-back failures. 2. The email stays in the analyst's queue, the failure is captured in the audit trail, and the item is surfaced as an exception. 3. The reason for the failure is shown explicitly on screen, so the analyst knows the item needs working manually. 4. The analyst works the email through the existing manual workflow until the cause is fixed. | 9.2(10) | Overlaps | F-01. Shares the alerting mechanism introduced in F-01. | Partially done | The item is never lost and the bsmdev Exceptions view surfaces the failures as an analyst-readable queue with the reason - Nothing extracted (9), Partial extraction (2), Dropped as irrelevant with the reason joined from the audit trail (35). Missing: no failure event type in the audit store, and settlement-system and write-back failures are not covered because no write-back exists.
F-70 [overlaps F-02, F-68] | Part C. Cross-cutting features | C3. Resilience and failure handling | OTC Allege pilot | System | Medium | Containment controls when the AI misbehaves | Provide the levers needed to contain a badly performing AI component. | 1. Disable the affected AI component (like comapre n match or unstrucured to structured ) and revert that step to manual handling. 2. Reduce the routing percentage to limit further exposure. 3. Fail over to a previous model version. | 12.5 | Overlaps | F-02, F-68. Uses the routing setting in F-02 and the version rollback in F-68. | Partially done | Only the model fail-over lever exists, via a platform property read per call - and the change is not audited. Missing: no switch to disable an AI component and revert that step to manual, and no routing percentage to reduce exposure.
W-01 [overlaps F-54] | Part D. Work Driver Onboarding Wizard features | D1. Access and landing | Work Driver Onboarding Wizard | All roles | High | Drive what a user can do from their role | Take each user's role and their assigned activities from the firm's role directory, and let that decide what they can do. | 1. Managers create, validate, publish, version and assign wizards. 2. Analysts only work the activities assigned to them and do not build wizards. 3. Users sign in through enterprise single sign-on. | Wizard 7.1 FR-1.1, 5 Assumptions | Overlaps | F-54. Same access model, at platform level. | Done | AccessGuard plus the manager and analyst roles gate every surface; the wizard read ACL calls the guard, and the login widget is SSO-only whenever an identity provider is set.
W-02 | Part D. Work Driver Onboarding Wizard features | D1. Access and landing | Work Driver Onboarding Wizard | All roles | Medium | Send each user to the right landing screen | Open the screen that matches the user's role on login. | 1. A manager lands on the wizard management view. 2. An analyst with one assigned activity goes straight into that activity's dashboard. 3. An analyst with more than one assigned activity sees a card per activity and picks one to open. 4. An analyst sees only the activities for the wizards assigned to them. | Wizard 7.1 FR-1.2 and FR-1.3, UC-7, 10 | Unique |  | Partially done | Managers are redirected to the manager dashboard; analysts get one card per assigned published wizard. Missing: a single assigned activity still renders the card grid, with no auto-open of its dashboard (FR-1.2).
W-03 | Part D. Work Driver Onboarding Wizard features | D2. Manager: managing wizards | Work Driver Onboarding Wizard | Manager | High | Wizard list split into Published and Drafts | Show the manager their wizards in two groups so work in progress is separate from what is live. | 1. Search and filter by work driver and by activity. | Wizard 7.2 FR-2.1 and FR-2.2 | Unique |  | Partially done | The wizard list splits Published and Drafts with counts and a name search. Missing the work-driver and activity filters: the row filter and the option lists are both built, but no control is rendered.
W-04 | Part D. Work Driver Onboarding Wizard features | D2. Manager: managing wizards | Work Driver Onboarding Wizard | Manager | High | Start a new wizard from scratch or from a copy | Offer two routes when the manager creates a wizard. | 1. Create new. 2. Copy an existing wizard, adjust it, and save it as the starting point for the new one. | Wizard 7.2 FR-2.3, UC-1, UC-2 | Unique |  | Done | The list's Create modal offers Create new and Copy & edit existing; the builder loads the copy as a clone named "<name> (copy)" and leaves the source record untouched.
W-05 | Part D. Work Driver Onboarding Wizard features | D2. Manager: managing wizards | Work Driver Onboarding Wizard | Manager | High | Manage a wizard through its life | Let the manager act on an existing wizard. | 1. Edit, publish, unpublish, version and delete. 2. Editing and unpublishing are available on a wizard that is already live. | Wizard 7.2 FR-2.4, UC-6 | Unique |  | Partially done | Cards give Edit, Delete, Publish (drafts) and a gear Settings editor. Missing: there is no Unpublish control anywhere, and the version is only a free-text string on the Settings modal.
W-06 | Part D. Work Driver Onboarding Wizard features | D2. Manager: managing wizards | Work Driver Onboarding Wizard | Manager | High | Assign a published wizard to analysts | Let the manager pick named analysts from the role directory and assign a published wizard to them. | 1. Assignment is by individual user, not by team. | Wizard 7.2 FR-2.5, 7.5 FR-5.2, UC-5 | Unique |  | Done | The Assign modal on published cards checkbox-picks individual users, writes the assignee list and count and grants the analyst role; the pick list is filtered by the demo-users property rather than the whole directory.
W-07 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | High | Step 1, Define the activity | Capture what the activity is. | 1. Fields: name, description, BU, Sub-BU, work driver, activity. 2. Name, work driver and activity are mandatory. | Wizard 7.3 FR-3.1 | Unique |  | Done | Step 1 captures name, description and the cascading BU / Sub-BU / work driver / activity / skill; Next is blocked until the name and the full taxonomy are set and the activity has a pre-coded step set. (Three builder labels are shifted one level against the BRD vocabulary - substance is right, naming is inverted.)
W-08 [overlaps F-05, F-09] | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | High | Step 2, Set the input source | Capture where the work comes in from and how often to look. | 1. Select the input format, then select the source for that format: a mailbox, a shared folder path, or a source system. 2. Set the frequency at which the source is checked. 3. For email, capture one or more identification rules, each holding context, keywords, sender emails, a subject pattern, and exclusion emails. 4. The input source model is extensible, so a new input type can be added without rebuilding this step. 5. Still to be decided: what a product template holds and where it is offered in the builder; the BRD line that introduces templates is incomplete. | Wizard 7.3 FR-3.2, 8 | Overlaps | F-05, F-09. The wizard form for the identification rules the Allege flow applies. | Partially done | Step 2 captures ingestion type, mailbox, frequency and one identification rule (context / keywords / senders / subject / exclusions plus 3 toggles). Missing: no input-format or folder/system source, and the Add-rule button is unwired so only one rule is possible.
W-09 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | Medium | Generate the extraction prompt for the manager instead of relying on their wording | A manager configuring a new activity should not have to know how to write a prompt for the AI. The builder offers to draft it from what they have already filled in. | 1. An enhance option on the input form drafts the prompt from the activity, the input source, the field list and any sample the manager has uploaded. 2. The manager can read, edit and overwrite the draft; nothing is published without them accepting it. 3. The prompt is versioned with the wizard, so the audit trail shows which prompt text produced which extraction. 4. Where a sample input is supplied, show the fields the drafted prompt actually pulled out so the manager can judge it before publishing. 5. Removes the dependence on the manager's own prompt-writing skill, which otherwise varies wizard by wizard. | Wizard FR-3.2, FR-3.5 | Unique |  | Partially done | The prompt enhancer rewrites a prompt, description or context via the LLM, manager-editable, and the catalogue fields ship with prompts. Missing: it requires an existing draft - nothing drafts one from the activity, source or sample. The cited BRD refs do not actually cover prompt drafting.
W-10 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | High | Step 3, Choose the target systems and map the fields | Capture what the extracted data is compared against and how the fields line up. | 1. Select up to five target systems. 2. For each target system, map every input field to a target field. 3. Alternatively define a calculated field that combines input fields using an operator. | Wizard 7.3 FR-3.3, 8 | Unique |  | Partially done | Target Mapping maps each input field to a target column with auto-map and an extract-only list. Missing: only ONE target system is possible (the Add-target button is inert) and there is no calculated/operator field.
W-11 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | High | Step 4, Review the configuration | Show the manager a summary of the whole configuration to check before going further. | 1. Show the activity definition, the input source and its rules, the fields, the target systems and the mapping, on one screen. 2. Flag anything incomplete or inconsistent before the manager can move on. 3. Allow the manager to jump back to any earlier step from the summary and return. | Wizard 7.3 FR-3.4 | Unique |  | Partially done | Step 3 Review summarises definition, ingestion, field count, mapping, write-back and tolerances. Missing: nothing is flagged as incomplete (Next is unconditional here) and the stepper has no click handler to jump back.
W-12 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | Medium | Step 5, Run a test and validate | Run a test comparison so the manager can see the wizard work before publishing it. | 1. The test runs on the first email or work item from the configured input source. 2. Show a field-by-field match with a confidence score, and show any mismatches. 3. The manager can change the configuration and run the test again before publishing. | Wizard 7.3 FR-3.5, UC-3 | Unique |  | Partially done | Step 4 runs the configured field prompts over PASTED sample text and can be re-run. Missing: it never reads the first mail from the configured source, and shows no confidence and no mismatch.
W-13 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | Low | Help on every field | Give each field in the builder an information tooltip explaining what it is for. | 1. Every field in the builder carries an information tooltip saying what it is for and what a valid entry looks like. 2. Written for a manager who does not build wizards often, so no technical vocabulary without an explanation. | Wizard 7.3 FR-3.6, 9 | Unique |  | Partially done | Each sub-step carries a descriptive sub-heading and each tolerance row a hint. Missing: no per-field information tooltip - every tooltip in the builder is on a button, not a field.
W-14 | Part D. Work Driver Onboarding Wizard features | D3. Manager: the wizard builder | Work Driver Onboarding Wizard | Manager | Medium | Save as a draft at any point | Let the manager save an incomplete wizard as a draft and come back to it. | 1. Drafts appear in the Drafts group on the wizard list. | Wizard UC-1, 7.2 FR-2.1 | Unique |  | Done | A silent draft save fires on every step advance, exiting auto-saves an unfinished wizard, and there is an explicit Save as draft on step 4; anything not published lands in the list's Drafts group.
W-15 | Part D. Work Driver Onboarding Wizard features | D4. Publish and version | Work Driver Onboarding Wizard | Manager | High | Publish a wizard and version it on republish | Publishing makes a wizard available to be assigned. | 1. Republishing a wizard that is already published increments its version. | Wizard 7.5 FR-5.1, UC-4 | Unique |  | Partially done | Publish sets the status the analyst surfaces query. Missing the increment: the builder writes version = existing or 'v1' on every save, so republishing never bumps it, and there is no version history, snapshot or rollback.
W-16 | Part D. Work Driver Onboarding Wizard features | D4. Publish and version | Work Driver Onboarding Wizard | Manager | High | Stop a second wizard being published for the same condition set | Two published wizards that both claim the same input can both pick up the same item, so the platform has to refuse the duplicate at publish time. | 1. A condition set is what decides whether an item belongs to this wizard: the input source, the sender or folder rules, the activity, and the identification conditions. 2. On publish, compare the condition set against every published wizard and block an exact duplicate. 3. Where the condition sets only partly overlap, warn the manager, name the other wizard, and require confirmation before publishing. 4. A new version of the same wizard is not a duplicate; the check is against other wizards. 5. At run time, if an item still satisfies two wizards, hold it as an exception and mention on the analyst interface rather than processing it twice. | Wizard FR-2.4, FR-5.1 | Unique |  | Not in BRD | Neither FR-2.4 nor FR-5.1 mentions a condition set, and nothing else in the BRD does. Also unbuilt: the publish path makes no comparison against other published wizards' identification rules, so an overlap is never held as an exception.
W-17 [overlaps F-05, F-07] | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | System | High | Find the item to act on in the source | At run time, identify the relevant item in the configured source, for example the relevant email in a mailbox or the relevant TRAM message. | 1. Uses the identification rules captured in the wizard. | Wizard 7.4 FR-4.1 | Overlaps | F-05, F-07. The generic form of the Allege identification step. | Done | identify() applies the published driver's identification rules - structural toggles, keyword/subject/sender rules, then AI context - with no code change; the routing verdict is persisted and audited.
W-18 [overlaps F-14, F-16] | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | System | High | Turn the unstructured input into structured data | Convert the item into a structured representation held as JSON. | 1. Produce one structured JSON record per item, i.e. a machine-readable form of what was extracted. 2. The structure follows the field list the manager configured in the wizard, not a fixed schema. 3. Everything downstream, matching and the screens, works from this structured form. 4. Keep the original input alongside it for audit. | Wizard 7.4 FR-4.2, 8 | Overlaps | F-14, F-16. The generic form of the Allege extraction step. | Partially done | The LLM returns wizard-keyed JSON rows and the .eml is kept, but only the fixed 13 catalogue columns are stored - custom fields are dropped. The generic structured-JSON column exists on the work-item table, which the live mail pipeline does not use.
W-19 [overlaps F-14, F-16, F-20] | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | System | High | Extract the fields the wizard was configured with | Pull out the configured fields, AI-assisted. | 1. Covers classifying the email and extracting the attributes. | Wizard 7.4 FR-4.3, 5 Dependencies | Overlaps | F-14, F-16, F-20. The generic form of the Allege extraction and confidence scoring. | Done | identify() classifies via the rules plus an LLM label-context match; the instruction builder turns each field's prompt and examples into the live instruction; confidence is scored per field.
W-20 [overlaps F-25, F-26, F-27] | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | System | High | Match the extracted data against the target system | Compare the extracted data against the configured target system and return the result field by field. | 1. Includes fuzzy matching. 2. Produce a confidence score with the result. | Wizard 7.4 FR-4.4 | Overlaps | F-25, F-26, F-27. The generic form of the Allege tiered matcher. | Partially done | The matcher loads the driver's tolerances, runs Tier 1/2/3 with fuzzy names, and stores confidence plus field-level diffs. Missing: the target system and mapping are written by the builder but never read at run time - the matcher always queries the local booking table.
W-21 [overlaps F-23, F-33] | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | System | High | Flag mismatches and exceptions for the analyst | Surface anything that did not match, and anything that failed, for analyst review. | 1. Where the match finds nothing, or finds something with differences, surface it to the assigned analyst rather than closing it. 2. Where processing fails, surface the failure with its reason on screen, and keep the item. 3. Show what was expected against what was found, field by field. | Wizard 7.4 FR-4.5 | Overlaps | F-23, F-33. The generic form of the Allege exception and outcome surfacing. | Done | A field-by-field expected-vs-found panel pair, a no-match banner and ranked candidates; the board shows the diagnostic on error and the funnel notes that mails are never dropped.
W-22 | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | Manager | High | Hold the Allege matching behaviour as wizard configuration | Because Phase 1 builds the Allege flow as a wizard configuration, the matching behaviour the Allege flow needs has to be expressible in the wizard rather than written into it. | 1. Everything the Allege flow needs is configuration driven; no Allege behaviour is written into the engine. 2. The tier cascade: exact, then tolerance, then a search with the counterparty filter dropped. 3. Per-field tolerances, including a fuzzy name match and a business day window with its holiday calendars. 4. Candidate ranking. | Allege 7.7, wizard 7.3 FR-3.3 | Unique |  | Partially done | Only three Tier-2 numbers are wizard config (value-date days, absolute amount, name fuzzy percent). The tier cascade and candidate ranking are hard-coded, and there is no holiday calendar - weekends only.
W-23 | Part D. Work Driver Onboarding Wizard features | D5. Run-time engine: identify, extract, match | Work Driver Onboarding Wizard | Manager | High | Hold the target actions a work driver needs, not only the match | The Allege flow tags Outlook and writes back to NEWS and PCM, so the wizard has to carry target actions as well as target systems for matching. | 1. Apply and update a tag on the source item, for example the Outlook tag and its four values. 2. Write back to a target system under the analyst's identity on analyst confirmation. 3. Configuration driven like the rest. | Allege 7.4 and 7.8, wizard 7.3 FR-3.3 | Unique |  | Partially done | The wizard stores a tag per stage and actions per outcome, but neither executes - tagging is read only by the builder, write-back is display-only, and the route step does no external write.
W-24 [overlaps F-42] | Part D. Work Driver Onboarding Wizard features | D6. Analyst | Work Driver Onboarding Wizard | Analyst | High | Work the assigned activity from its dashboard | Give the analyst the working surface for each activity assigned to them. | 1. One assigned activity opens its dashboard directly; several show a card per activity. 2. The analyst reviews the AI-assisted output and acts on it; the review points are mandatory and are not skipped. | Wizard UC-7, 5 Constraints, 10 | Overlaps | F-42. The generic form of the Allege analyst working screen. | Partially done | The work-driver page builds one card per assigned published driver and the board enforces confirm-then-match gates, but a single assigned activity still renders the card grid instead of opening its dashboard (FR-1.2).
W-25 [overlaps F-54] | Part D. Work Driver Onboarding Wizard features | D7. Admin and IT | Work Driver Onboarding Wizard | Admin / IT | High | Manage users, roles and access | Give the admin control of who can use the platform and what they can do. | 1. Includes controlling who is allowed to author wizards. | Wizard UC-8, 3 | Overlaps | F-54. Same access model, at platform level. | Partially done | Authoring is gated to the manager role and Assign grants the analyst role. Missing: no in-app user/role admin surface, no Admin role, and the assignee pick list comes from the demo-users property.
W-26 | Part D. Work Driver Onboarding Wizard features | D7. Admin and IT | Work Driver Onboarding Wizard | Admin / IT | Low | Show platform health and uptime to IT | Make the platform's availability and health visible so IT can monitor it. | 1. Show whether the platform is up, and the uptime against the service expectation. 2. Show the health of each configured integration, so IT can see which target system is failing. 3. Show the processing backlog and any stuck items. | Wizard UC-9, 9 | Unique |  | Partially done | The wizard board shows a pending/errored backlog and the LLM observability page shows success rate, p50/p95 latency and failures. Missing: uptime against a stated service expectation, and per-integration health.
W-27 [overlaps F-60] | Part D. Work Driver Onboarding Wizard features | D8. Audit and governance | Work Driver Onboarding Wizard | System | Medium | Audit trail of changes to a wizard | Record every change through a wizard's life, with who made it and when. | 1. Covers create, edit, publish, unpublish, version and assign. | Wizard 7.6 FR-6.1 | Overlaps | F-60. Audit capture at wizard level, on the same store. | Partially done | Native record auditing on the wizard table (bsmdev, 26 Sept) now captures every field change with old value, new value, actor and timestamp, on top of the record's created/updated-by stamps. Missing: no in-app wizard lifecycle event (create/publish/version), and the native trail is admin-only - it is not reachable from the portal.
W-28 [overlaps F-60] | Part D. Work Driver Onboarding Wizard features | D8. Audit and governance | Work Driver Onboarding Wizard | System | High | Audit trail per processed item | Record, for every item the platform processes, who did what and when. | 1. For every item the platform processes: what came in, what the AI recommended, what the analyst confirmed or corrected, what was written back, with identity and timestamp on each. 2. Held in the same audit store as F-60. 3. Retrievable per item, so a single item's history can be produced on request. | Wizard 7.6 FR-6.2, 9 | Overlaps | F-60. Audit capture per item, on the same store. | Done | Per-item audit rows cover classification, extraction (with model, prompt reference, input hash and confidence), confirm and override, match computed/selected/confirmed, and write-back - all retrievable per item.
W-29 [overlaps F-24, F-44] | Part D. Work Driver Onboarding Wizard features | D8. Audit and governance | Work Driver Onboarding Wizard | System | High | Keep the human review points in place end to end | Preserve the human-in-the-loop checkpoints throughout, on every AI-assisted step. | 1. Every AI-assisted step has a named human confirmation point before anything is committed. 2. No configuration can switch a confirmation point off; a wizard cannot be published as fully automatic. 3. The confirmation is recorded, so the trail shows a person acted. | Wizard 7.6 FR-6.3, 5 Constraints | Overlaps | F-24, F-44. The human-in-the-loop principle already built into F-24 and F-44. | Partially done | Compare & Match runs only after confirmation and write-back only after review confirmation, both audited, with no disable toggle. Gap: the AI classification step auto-commits relevant/irrelevant with no human gate, and dropped mail reaches no analyst surface in this codebase (the bsmdev Exceptions view now covers that).
W-30 [overlaps F-21] | Part D. Work Driver Onboarding Wizard features | D9. Data handling | Work Driver Onboarding Wizard | System | Medium | Configurable input types and target systems | Hold the input types and the target systems as configuration rather than as code. | 1. Input types supported: email, TRAM message, PDF, Excel and shared-folder files, extensible to new types. 2. Extracted data is held as structured JSON. 3. Each target system exposes the field set used for matching. 4. The mapping model links each input field either to a target field or to a calculated field. 5. Data handling follows the firm's security, retention and governance standards. | Wizard 8, 5 Assumptions | Overlaps | F-21. Structured representation and standardisation of the extracted data. | Partially done | The builder holds input formats (Email/PDF/Excel), ingestion types, target systems with their field sets, and per-field mapping. Missing: TRAM and shared-folder types, calculated-field mapping, and any retention or encryption control. At run time the pipeline is .eml-only - the stored input format and ingestion type are never read.
Note on A1: F-xx are OTC Allege pilot features, W-xx are Work Driver Onboarding Wizard features. [repeat of X] means do not build it separately. [overlaps X] means build it once with X.
Note on F1: High: the pilot cannot run without it. Medium: needed before the solution can scale up. Low: can be deferred, analysts keep handling it manually.
Note on I1: A yellow cell means this feature still has something undecided; the last numbered line says what.
Note on K1: Filter on Unique and Overlaps to get the build list; Repeat rows are already covered elsewhere.